## Sheet1
# | item | category | Work package cost($AUD) | Work Package contingency reserve(AUD$)
1 | labor costs | general | 2400 | 240
2 | Website design and construction | administrators | 20000 | 2000
3 | Website testing and maintenance | administrators | 10000 | 1000
4 | Manager training | administrators | 6000 | 600
5 | Manager incentive bonus | administrators | 5000 | 0
6 | Discover user costs | users | 10000 | 500
7 | users incentive bonus | users | 10000 | 0
8 | User training | users | 5500 | 1200
9 | Offline events held | users | 5000 | 2000
Total budget($AUD) | 83500 | / | / | /
# | item | category | Activity start | Activity end | Duration(Day)
1 | labor costs | general | 2021/2/15(week1) | 2021/5/7(week4) | 20
2 | Website design and construction | administrators | 2021/2/15(week1) | 2021/3/15(week5) | 28
3 | Website testing and maintenance | administrators | 2021/3/15(week5) | 2021/3/31(week6) | 7
4 | Manager training | administrators | 2021/4/1(week7) | 2021/4/7(week8) | 7
5 | Manager incentive bonus | administrators | 2021/4/7(week8) | 2021/5/7(week12) | 30
6 | Discover user costs | users | 2021/2/25(week3) | 2021/3/31(week6) | 35
7 | users incentive bonus | users | 2021/4/1(week7) | 2021/5/7(week12) | 37
8 | User training | users | 2021/4/1(week7) | 2021/5/7(week12) | 37
9 | Offline events held | users | 2021/4/1(week7) | 2021/5/7(week12) | 37